M1-11: Risk Register

Risk Priority Matrix:

Low Priority <= 2

Medium Priority > 2 & <=5

High Priority >5

Probability

Impact

|  | Low | Medium | High |
| --- | --- | --- | --- |
| Low | Low | Low | Medium |
| Medium | Low | Medium | High |
| High | Medium | High | High |

Risk Register:

| Risk ID | Description | Cause | Probability | Impact | Priority | Mitigation | Contingency | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R-001 | Teammate unable to work, Max 3-person team constraint CON-003 | Poor Health/Unfortunate Unforeseen Complications | Medium | High | High | Cross training so other teammates can pick up slack. | Unable to add team members to project. Remaining teammates will have to work under increased load to make up for lack of teammate until situation can be rectified. Otherwise, renegotiation with stakeholders about replacement team member under severe complications. | Project Team | Open |
| R-002 | Unrealistic Scope, Scope Constraint and Time Constraint, if CON-001 is not adhered to. | Team may become too ambitious in defining the scope so as to create too much work resulting in the project not being able to be completed in the allocated time | Medium | High | High | Team must agree on scope that meets base stakeholder expectations and requirements. Such as a MVP (Minimal Viable Product) If this is noticed to be achievable during later stages improvement of scope to enhance product with nice to haves can be considered under strict change control processes. | If initial scope is found to be too much change control processes must be followed to reduce scope so that unnecessary items that are not needed for the success of the project can be eliminated. | Stakeholder and Scope Lead | Open |
| R-003 | FS-003 Built system may use technologies that are incompatible with external system making it unable to integrate | Lack of consideration of integration between systems when designing the system and choosing the technologies and architecture to be used. | Low | High | Medium | Team must take into consideration the integration into the full system and make the decisions regarding design based on constraints and requirements and ensure that technologies can work together. | Project system will have to be reworked so that it will be able to integrate however this will impact time constraint heavily as the project will fail to be completed in time resulting in failure. | Stakeholder and Scope Lead. | Open |
| R-004 | ASM-006 Suitable stakeholders may not be frequently available to clarify needs and review the team’s interpretation of the CivicConnect process. | Stakeholder unavailability | Medium | Medium | Medium | Make the interactions with stakeholders meaningful so that information gained is sufficient if it comes down to them being unavailable | Team may need to conduct its own research into the company with lack of stakeholders but may not be as effective as actual stakeholder engagement. | Project Team | Open |
| R-005 | CON-006 ASM-004 Security may be impacted and requester may be able to complete tasks they should not and access information they should not. | Lack of defined user roles and responsibilities. | Low | High | Medium | Proper stakeholder engagement to create well-defined user roles. | Research into similar platforms to identify roles and the responsibilities and access they have. | Requirements and Security Lead. | Open |
| R-006 | SC-002 ASM-002 FR-002 Service request categories may be insufficient or irrelevant resulting in could cause requests to be misclassified and make reports unreliable. | Categories are not well defined and derived from relevant stakeholders. | Low | Medium | Low | Sufficient engagement with stakeholders to derive relevant proper categories. | Research into the types of requests users usually make using old data from CivicConnect if stakeholders aren’t available. To derive proper categories. | Stakeholder and Scope Lead. | Open |
| R-007 | SC-004 ASM-003 FR-003 Request statuses and request lifecycle phases are ill-defined resulting in system creation that may not meet needs or expected workflow. | Request statuses and lifecycle phases are ill-defined. | Low | Medium | Low | Significant engagement with stakeholders to derive well defined request statuses, lifecycle and workflow. | Research and observation of CivicConnect working environment to discover and understand workflows to create a meaningful system in the absence of stakeholder help and engagement. | Requirements Lead | Open |
| R-008 | ASM-001 FS-001 Requester may not have access to a suitable device, supported browser and sufficiently reliable internet connection when using CivicConnect. Please note this is deferred scope and not a priority. | Stakeholders might lack the resources to access platform and team did not cater to this. | Low | Low | Low | When designing and implementing choose relevant tech stacks and architecture so that the app is easily available to most requesters. Possible implementation of offline system in case of some requesters not having the basic resources needed which is unlikely. | Development making the system available offline which is unlikely. | Requirements Lead | Open |
| R-009 | AI-assisted content may contain unverified or incorrect assumptions if not independently checked | Team member negligence is verifying ai generated work. | Low | Medium | Low | Governance through github makes it that work needs to have two reviewers who have to sign off on the merge so this can be detected and rejected by other teammates. | If teammate refuses to fix it other teammates will have to take over work and inform relevant stakeholders so that teammate can be dealt with. | Project Team. | Open |
| R-010 |  |  |  |  |  |  |  | Project Team | Open |
| R-011 |  |  |  |  |  |  |  | Project Team | Open |
| R-012 |  |  |  |  |  |  |  | Project Team | Open |
| R-013 | A privileged Supabase secret could be exposed. | Incorrect environment configuration between development, preview and production. | Medium | High | High | Keep environment settings separate and verify them during deployment testing. | Correct the environment configuration and redeploy the affected version. | Project Team | Open |
| R-014 | A privileged Supabase secret could be exposed if it is placed in frontend code or committed to Git. | A secret key is accidentally placed in frontend code or committed to Git. | Low | High | Medium | Only use the publishable key in frontend code and keep privileged secrets out of source control. | Revoke and replace the exposed key immediately and review access for suspicious activity. | Project Team | Open |
| R-015 | CivicConnect could be affected by Vercel or Supabase availability, service limits or pricing changes. | The proposed deployment depends on external hosted services. | Low | Medium | Medium | Review service limits and production requirements before launch and monitor relevant platform changes | Reconsider the hosting option or service plan if the selected platforms no longer meet project needs. | Project Team | Open |
| R-016 | A deployment may build successfully but still have problems with authentication, routing or RLS outside local development. | Some issues may only appear in the deployed environment rather than during local development. | Medium | High | High | Test login, role access, routing and important user flows in the deployed environment before production promotion. | Roll back the affected deployment and correct the configuration or application issue before redeploying. | Project Team | Open |