## Sheet1
Engineering Decision Log
Decision ID | Context | Constraints | Alternatives | Decision | Rationale | Trade-Offs | Risks | Evidence | Later Consequence
DEC-001 | FS-001 | CON-001 | Mobile native app in scope to be developed. WhatsApp, SMS and email service integration into the system. | Deferment of decision to include these features they are labelled as deferred scope. | The constraint of time with regard to size of the scope, resources being under low to no cost, while also choosing a suitable technology platforms to create a quality product. Promotes the decision that these are nice to haves and should be deferred for now. | Project will lack accessibility through various platforms such as mobile. And will have no integration with WhatsApp, SMS and email services. | Risks associated with trying to implement them involve inability to complete project within constraint. | The current scope is sufficient for now and these have been placed under deferred scope as if implemented they may not meet the mentioned constraints. | No major identifiable consequence as current scope meets business need.
| FS-002 | CON-002 | [6 empty] | Also, the ability to implement these later might be lost as they were not considered properly leading to incompatibility with the system.
| FS-003 | CON-004 | [6 empty] | Stakeholders would have possibly enjoyed these add-ons.
| Digital platform needs to be accessible to requesters and stakeholders | CON-005
CON-007
DEC-002 | Tech stack and architecture decisions for design and implementation | CON-004 | No alternatives as due to constraints the decision has to be deferred to M2 | Deferment of decision to M2 | After more research has been done during the process of M2 sufficient information will be available to make a suitable decision. | Loss of time CON-002 as we wait for M2 brief | No major risks possibility of procrastinating the start of M2 could affect the decision and overall project, that can be managed. | CON-007 states that decision should be deferred until sufficient information is available, such as when M2 starts. | No major later consequence other than the possibility of a late decision impacting the time constraint.
CON-007
M2 update: technology stack resolved by DEC-008 / ADR-001; architecture is handled separately.
DEC-003 | FS-004 | CON-001 | Include in scope rather than deferred scope. | Label as Deferred scope, decision to implement is left for the future. | Implementation of feature may impact time constraint and scope as working on this may take away from the actual functionality involving business needs. | Project will be done in time but wont have this feature. | No major risks as not including this feature does not impact what the business requires of the digital platform. | Business need, Problem statement. Requirements and current scope. As well as time constraint. | No major later consequence, besides possibly the decision to defer implementing this feature could lead to the inability to include this feature due to compatibility with the system.
| AI request categorisation and prioritisation | CON-002
CON-004
CON-005
CON-007
DEC-004 | Practicing using Github and branch protection and PR during milestone 1 documentation | CON-008 | Creating milestone 1 as its own document and not using Github features to construct govern and verify documents | Using Github throughout milestone 1 instead of just when coding starts | Constraint in project that documents must be governed and managed through repo | New gained experience that will benefit the team later in the project as team has practiced and now understand how to use all these github functionalities. | No major risk. Helped team learn github. | CON-008 | No major later consequence as learning to use github is needed as github version control and tracking as well as accountability is a requirement.
|  | Academic and project governance | [5 empty] | States that documentation must be managed through Github repository.
ADR/DEC-005 | Select a persistence model for CivicConnect's structured relational data. | Fixed relationships, data integrity, transactions, low–moderate scale, team capacity and cost. | PostgreSQL/Supabase. NoSQL/document database | Use PostgreSQL through Supabase as the relational persistence solution. | Supports foreign keys, transactions, strong consistency, structured queries and the ERD relationships. Supabase reduces database-management overhead. | Requires a defined schema and creates dependency on Supabase. | R-011 Availability, backup/recovery and scaling depend on the selected Supabase configuration. | CivicConnect ERD. M2 persistence requirements. Relevant A2 persistence research. | R-011. Reassess scaling, backup and hosting configuration if usage or availability requirements increase.
DEC-006 | M2-10 technology stack decision; resolves the technology part of DEC-002. | CON-003 | React vs plain JS; Supabase vs Node/Express; Figma-first vs design in code. | React/Vite + Supabase/PostgreSQL; Supabase Auth; RBAC/RLS planned; Figma manual design; GitHub Actions CI. Node.js tooling only. | Fits relational data, team capacity and cost, and is supported by M2-13 implementation. | Supabase learning/vendor dependency; auth/live DB/RLS pending; custom backend may be needed later. | R-010 to R-012 | ADR-001; M2-10; M2-13; M2-12 PR #77; M2-11. | Use controlled change and update ADR-001 / Decision Log if the stack materially changes.
CON-004
CON-007
M2-02 ASRs
ADR/DEC-007 | Decide whether in-app notifications require their own persistent database entity. | Current requirements focus on status-change notifications. The system should avoid unnecessary persistence structures. | 1. Create a dedicated Notification entity. 2. Use transient in-app notifications triggered by status changes. 3. Store notifications as part of Comments. | Do not create a dedicated Notification entity under the current scope. | The current requirements focus on notifying the requester of status changes; the current status and request_status_history provide the persistent record. | Keeps the data model simpler, but notification delivery/read history is not retained. | Future external messaging may require persistent delivery records. | Current requirements, ERD and API/integration decisions. | Reassess if SMS/WhatsApp/email integration or notification history becomes required.
ADR/DEC-008 | Define how the Requester/Staff UI communicates with the Backend Request Handler Service. | The system requires request submission, status/history retrieval, staff status updates and filtered queries. Authentication, authorisation and server-side validation must also be enforced. | 1. HTTP/REST API. 2. Direct database access from the client. | Use an HTTP/REST API between the client and Backend Request Handler Service. | The client and backend operate across separate runtime boundaries, making an HTTP API an appropriate integration mechanism. REST also supports the required request/response interactions and aligns with the A2 Task 3 REST research. | Provides a clear separation between client and backend, but introduces network communication and requires API validation, error handling and authentication. | Network failures, invalid requests, unauthorised access and breaking API changes could affect client–backend communication. | A2 Task 3 REST research and evaluation, FR-001, FR-003, FR-010 and NFR-001. | Breaking request/response changes will require coordinated deployment or API versioning if multiple clients or independently deployed consumers are introduced.
ADR/DEC-009 | Define how a completed service-request status update produces an in-app notification for the relevant requester. | The notification should only be produced after the service-request status has been successfully updated and the corresponding status-history record has been created. No unnecessary network boundary should be introduced. | 1. In-process asynchronous event using the Observer pattern. 2. HTTP API between the Request Handler and Notification component. | Use an in-process asynchronous event using the Observer pattern to notify the relevant requester. | The components are within the same deployable application, so an HTTP/network boundary would add unnecessary complexity. The event-based approach also allows future notification consumers to be added without changing the status-update producer. | Avoids network overhead and keeps the components decoupled, but notification delivery is dependent on the application process and is not persisted under the current scope. | A notification may not be delivered if the application process fails after the status update. Future external messaging will introduce additional integration and delivery risks. | A2 Task 3 mechanism comparison, updated ERD, DEC-006 and the current notification requirements. | Future SMS, WhatsApp or email integrations can be added as additional consumers. If reliable delivery or delivery tracking becomes required, the notification design and persistence decision should be reassessed.
DEC-010 | M2-11 deployment compatibility and environment direction for the M2-10 technology stack. | CON-002 CON-004 CON-007; M2-02 scalability, cost, security and maintainability drivers. | Vercel + Supabase; Netlify + Supabase; custom hosting/backend infrastructure. | Use Vercel as the frontend hosting direction and Supabase as the managed backend/database direction. Keep Netlify as an alternative. Production deployment and full deployment automation are deferred. | This direction fits the implemented React/Vite client and Supabase/PostgreSQL baseline without adding unnecessary infrastructure. M2-13 builds locally and M2-12 verifies test/lint/build through GitHub Actions. | The project depends on hosted services; production limits, monitoring, recovery and exact deployment automation remain unresolved. | R-013, R-014, R-015 and R-016. | M2-11 Deployment Compatibility & Environment Direction; ADR-001; M2-10; M2-12 PR #77; M2-13 implementation evidence. | Before production, complete live persistence, authentication, role mapping/RLS, Vercel configuration and deployment-level testing. Review this decision if service limits, cost or future backend needs make the direction unsuitable.
DEC-011 | M2-12 requires a repeatable SCM and CI approach that supports the small-team review workflow. | M2-12; Assignment 2 Task 4; protected integration workflow; no committed secrets. | Manual verification only; CI with build only; CI with build/test/lint and progressive later checks. | Use GitHub-based CI to run repeatable automated verification for the implemented client and expose results during review. Automation supports rather than replaces human review. | Repeatable checks provide consistent evidence and fit the existing branch/PR workflow without adding unnecessary tooling. | CI requires maintenance as dependencies and project structure change; not every future security/dependency check is necessarily implemented at this stage. | R-017 and R-018. | M2-12 SCM & CI Adoption issue; CI workflow/evidence; related Pull Request and review evidence. | Expand checks progressively as meaningful implementation grows and reassess which checks must block integration.
DEC-012 | M2-13 marks the move from planning/baselining to meaningful CivicConnect-specific construction. | Approved M2 technology/deployment direction; M2-13 development and documentation requirements. | Remain at scaffold level; build isolated demo code; implement an initial CivicConnect functional path using the selected stack. | Proceed with project-specific React/Vite application work and initial persistence/interface/verification artefacts while documenting incomplete production-facing integration. | This demonstrates authentic construction against the approved M2 direction instead of empty scaffolding or a Hello World implementation. | The implementation is still incremental; production persistence, authentication/role controls, RLS and deployed behaviour require further work/evidence. | R-019 and R-020. | M2-13 Meaningful Development & Application Documentation issue; repository implementation; README/technical documentation; initial verification evidence. | Continue aligning repository structure and selected design decisions/patterns as development progresses, then verify the completed Supabase/auth/RLS path.
ADR/DEC-013 | M2-05- resolve excessive/unnecessary coupling between internal CivicConnect components (e.g. Request Processing, Notifications, Persistence) and integration with external/legacy municipal systems, per A2 Task 1 Design Problem 1. | CON-003, CON-004, CON-007, NFR-010. | 1. Dependency Inversion Principle (DIP) only. | Use DIP for internal CivicConnect component relationships, and the Adapter Pattern for integration with external/legacy municipal systems — scoped to different boundaries, not competing solutions for the same boundary. | DIP introduces additional interfaces/abstraction layers that must be scoped deliberately given CON-003's team size, rather than applied to every component. Adapter adds a translation layer per external integration that must be maintained as those external systems evolve. | DIP directly satisfies NFR-010 by letting internal components be tested/changed in isolation, and fits naturally within the modular monolith's in-process module boundaries (DEC-006). Adapter addresses the CON-004-shaped risk of external-system cost/timing/availability sitting outside the team's control, isolating interface differences so CivicConnect's core need not be redesigned if a legacy system changes. | Applying DIP too broadly could overcomplicate a small system (over-engineering risk raised in A2 §5). Creating an Adapter where no genuine interface incompatibility exists adds unnecessary components. Inconsistent application of DIP across modules could leave some internal dependencies still tightly coupled. | A2 Task 1 DIP/Adapter candidate evaluation; NFR-010; CON-003/CON-004/CON-007; DEC-006 modular monolith selection; M2-0X requirements/architecture/constraints comparison. | Each new internal module pairing added during implementation must be individually assessed for whether it needs interface-based decoupling. Each new external/legacy integration requires its own adapter to be built and maintained.
2. Adapter Pattern only. 3. DIP (internal) and Adapter (external boundary) applied together, scoped to different boundaries. 4. No pattern — retain direct concrete dependencies.
ADR/DEC-014 | M2-06- resolve CivicConnect components accumulating multiple unrelated responsibilities (business logic, validation, persistence, notification behaviour) within the same class/service, per A2 Task 1 Design Problem 2. | CON-003, NFR-010, FR-005, FR-010. | 1. Strategy Pattern only. | Use the Strategy Pattern as the primary approach for encapsulating alternative request-handling behaviours/decision rules; introduce the Facade Pattern later, and only where multiple related services genuinely need to be coordinated behind a simplified interface. | Strategy directly supports NFR-010 by letting each behaviour (e.g. prioritisation, routing, escalation) be developed, tested and changed independently, and A2's evaluation rated it Very Low coupling, Very High cohesion, and Excellent maintainability/extensibility/testability. Facade is reserved rather than adopted outright because CivicConnect has not yet evidenced enough coordinating complexity to justify it, consistent with CON-003's limit on how many patterns a 3-person team can build and maintain. | Strategy increases the number of classes in the codebase (one per behaviour), requiring consistent organisation/naming. Deferring Facade avoids premature abstraction, but a Facade will need retrofitting later if coordinating complexity does emerge, rather than being designed in from the start. | Building strategy classes for business rules CivicConnect doesn't actually have would be over-engineering (against CON-003). Missing an actual alternative-behaviour requirement could let conditional logic creep back into a component, reproducing the original design problem. | A2 Task 1 Strategy/Facade candidate evaluation; NFR-010; FR-005/FR-010; CON-003; DEC-006 modular monolith selection; M2-0X requirements/architecture/constraints comparison. | The final set of strategy classes to build must be confirmed against CivicConnect's actually-approved business rules, not A2's illustrative list. Revisit Facade if/when multiple services are shown to need coordinated access.
2. Facade Pattern only.
3. Strategy Pattern as primary approach, Facade introduced only where multiple services genuinely need coordinating. 4. No pattern — retain large components/embedded conditional logic.