## Sheet1
Forward Engineering Considerations Register
Concern ID | Why-Now | Downstream influence | Missing information | Risk-Of-Ignoring | Status
FEC-001 | FS-003 Integration with external municipal or organisational systems. | During M2 we will be designing the system and choosing which technologies we will be using to create the system we need to ensure that these technologies will work well when integrated with the existing systems. | The type of technologies the external system uses interfaces, permissions and compatibility information have not yet been established. | The team could end up building a system that cannot be integrated into the external system as the technologies are incompatible. | Open
Needs to be considered now as the system we make will need to work with these systems.
FEC-002 | ASM-002/SC-002 | When designing and implementing and building the system the team will need to know what controlled categories there are so they can be hardcoded for selection | The actual categories that will be available for requesters to choose are unknown for now | Categories will be undefined leading to uninformed decisions of the categories being made that could lead to requests to be misclassified and make reports unreliable. | Closed.
| The organisation will be able to provide and approve a controlled list of service-request categories. |  |  |  | Categories have been established.
Research or further investigation into what these categories are will need to be done.
FEC-003 | ASM-003/SC-004 | When designing and implementing the system there will need to be an understood process flow/lifecycle of requests and how they are resolved and what these statuses are throughout that lifecycle to make the system work meaningfully. | The statuses and flow of the request lifecycle are unknown so statuses at each phase are unknown. | Statuses of phases of the request lifecycle are unknown so the system flow will be unknown. Which will lead to unclear status rules could result in inconsistent updates, incorrect reporting and requirements that cannot be tested properly. | Semi-Closed.
| The organisation will be able to define the allowed request statuses and valid transitions between them. |  |  |  | Statuses have been defined lifecycle is not thoroughly understood but there is reasonable understanding.
Research into how requests are handled and the status phases that they go through may need to be conducted.
FEC-004 | FS-002 | Will be evaluated through a future scope change-request if stakeholder evidence justifies revisiting deferred scope in M3. | Whether scope can be completed efficiently enough in the current allocated time to allow for this extra feature to be implemented. | The app not having the integration with WhatsApp, SMS, and email services. | Semi-Open.
| The integration of WhatsApp, SMS and external email service. This needs to be considered for scalability purposes so as to make the app more accessible. |  |  |  | Due to ADR-009 implementing this has becoming much more considerable. Still looking into simulation for now though.
FEC-005 | ASM-004 | Affects authentication, role-based interface behaviour, database access, security testing and live persistence. Authenticated users still need to be mapped to the correct CivicConnect roles before RLS is enabled. | The final role-permission matrix, authenticated-user mapping and tested RLS policies are not complete yet. | Enabling access control without these rules could expose data or block legitimate users. Leaving the work too late could also delay live persistence. | Open.
| Requester, staff and management roles are identified, but the exact permission matrix and Supabase Auth/RLS rules still need to be finalised before database access control is enabled. |  |  |  | RBAC is introduced through use of supabase but roles still need to be comprehensively defined.
FEC-006 | ASM-007 | During the Design and Implementation phase the software/technologies and architecture selected need to take into consideration whether they can handle the number of users, requests and stored records. | How scalable the digital platform will need to be. As there is no information giving insight into the number of users, requests and stored requests there will be and how the system will need to perform under these loads. | The creation of digital platform that cannot scale and handle the load of users, requests and records while maintaining suitable performance. | Open
The expected number of users, requests and stored records will remain within the capabilities of the platform and services selected later.
This needs to be considered now for scalability purposes as it may influence the selection of the technologies and architecture used.
FEC-007 | ASM-008/CON-004 | Later deployment, scaling and operational decisions must check service limits and pricing before production use. A provider or plan change could affect the deployment baseline. | Expected production usage, required plan limits and the actual cost of deployed operation are not known yet. | Later service limits or costs could force a provider or plan change and affect the deployment approach or CON-004. | Open
React/Vite and Supabase have been selected for the current project, with Vercel as the current deployment direction. Free or low-cost options must remain sufficient during the project.
FEC-008 | M2-10 | If later features require substantial custom server-side processing, the backend architecture, interfaces, deployment and testing approach may need to change. | No current requirement proves that a dedicated custom backend is needed. Future processing and integration needs are still incomplete. | Discovering the need for a custom backend late could cause rework, integration changes and schedule pressure. | Open
Supabase is selected as the backend platform for the current scope, while Node.js/Express is retained only as an alternative if later needs justify it.
FEC-009 | M2-11 selects Vercel + Supabase as the deployment direction, but production deployment and the exact branch-to-environment mapping are not configured yet. | Later deployment work must define preview/production environments, environment-variable handling, deployment triggers and deployment-level verification without changing the approved branch/PR controls. | Final Vercel project configuration, domain/DNS choice, branch mapping and evidence from a tested deployed environment. | Leaving deployment configuration until the end without a controlled plan could cause environment mistakes, failed releases or behaviour that differs from local development. | Open
FEC-010 | M2-11 leaves production backup/recovery, monitoring, scaling and paid-plan decisions open because real production usage is not yet known. | These decisions will affect operational reliability, cost, capacity and production readiness once CivicConnect moves beyond the current student-project stage. | Expected production users/traffic/storage, recovery expectations, monitoring needs and current Vercel/Supabase plan limits. | Ignoring production operations could lead to inadequate recovery, unexpected costs, capacity problems or weak visibility of failures. | Open
FEC-011 | M2-12 introduces CI as repeatable support for review, but the current checks must evolve with the application. | Future development must keep build, test, lint/static analysis and any later dependency/security checks aligned with the actual stack and decide which checks should block integration. | Final test scope, later security/dependency tooling, branch-protection integration and evidence from subsequent development. | Out-of-date or weak CI could give reviewers false confidence or allow regressions into the integration branches. | Open
FEC-012 | M2-13 establishes meaningful initial implementation, but production-ready persistence, authentication/role controls and complete deployment behaviour are not all proven yet. | Later work must complete the functional path against the approved Supabase direction and verify role-based access, RLS and deployed behaviour. | Final user/role rules, completed Supabase integration, authentication behaviour, RLS policies and deployment-level verification. | Treating the initial implementation as complete could create security, data-integrity and traceability gaps. | Open
FEC-013 | The M2-13 ticket still requires the application structure and design decisions/pattern evidence to be demonstrably aligned with the approved engineering direction. | As more modules are added, the repository structure and implementation evidence must remain consistent with the architecture rather than growing ad hoc. | Final module boundaries, implementation of selected patterns/decisions and evidence from later feature work. | Architecture drift could increase coupling, make testing harder and weaken the evidence that implementation follows approved decisions. | Open
FEC-014 | Design Problem 1 pattern decision needs to be considered now because the decision to use DIP internally and Adapter at the municipal-system boundary has been made, but which specific internal module boundaries actually need an interface has not been finalised. | During implementation, every new interaction (e.g Request Processing, Notifications, Request Processing, Persistence) will need a decision on whether it goes through an interface or a direct call. | A confirmed list of which specific internal module pairs require interface-based decoupling versus which can remain direct calls, consistent with NFR-010 and the team-capacity limit raised in A2 (Assignment 2) | Developers apply DIP inconsistently across the codebase, module by module, as convenient rather than by design. | Open
FEC-015 | Design Problem 2 pattern decision (Strategy , and possibly Facade)- still being finalised. Needs to be considered now because A2's candidate strategy classes were named conceptually, not confirmed against CivicConnect's actual approved business rules. | During implementation, the exact set of strategies to build depends on CivicConnect's real request-handling rules (prioritisation, routing, escalation), which may not match A2's illustrative list. Whether Facade is added on top also still needs deciding and affects how many services a client component must coordinate directly. | The final, approved set of alternative request-handling behaviours/rules CivicConnect must support, and confirmation of whether enough coordinating complexity exits to justify a Facade in addition to strategy. | Building strategy classes for rules CivicConnect doesn't have (over-engineering, against CON-003), or missing a rule that does exit and failing back into embedded conditional logic the pattern was meant to avoid. | Open
FEC-016 | Architecture selection (Modular Monolith). Flagged as a residual risk during the M2-03 comparison against ASRs (Architecturally Significant Requirements) rather than treated as closed, because Scalability (NFR-011) was the one driver microservices served better, and this has not been retriggered by real usage yet. | If actual usage later exceeds the capacity test agreed for NFR-011, the architecture may need to evolve toward selective service extraction from the modular monolith rather than a full microservices rewrite — this needs to be planned for structurally (clean module boundaries now) so it's possible later, not reactive. | Real production usage data, since ASM-007/FEC-006 already shows expected user/request volume is unestablished — this entry specifically tracks the architectural consequence of that gap, not the platform/technology consequence FEC-006 already covers. | f internal modules aren't kept cleanly separated now (per NFR-010), a later need to extract a service under real load pressure becomes a much larger rework than if module boundaries were kept clean from the start. | Open
FEC-017 | Adapter Pattern selection for municipal/legacy system integration (Design Problem 1). Builds on FEC-001 (integration feasibility) but is a distinct, later-stage concern: once an adapter is built and working, it still needs upkeep as the external system changes. | Every adapter built for a legacy/external system becomes something the team must maintain going forward — if the municipal system's interface changes, the adapter (not the rest of CivicConnect) needs updating, but someone still has to notice the external change happened. | Whether the municipality will notify CivicConnect of interface/API changes to legacy systems, and how many separate adapters the team will realistically need to build and track given CON-003. | An external system changes silently, the adapter starts failing or silently passing bad data, and the team doesn't find out until a real integration breaks — directly undermining NFR-005 (Reliability). | Open
FEC-018 | NFR-009 (Auditability) implementation. Needs to be considered now because the exact audit-log schema (which fields, which actions, retention) has not been finalised, despite FR-005/FR-010 already being approved requirements that the audit log must support. | The audit-log structure affects the data model (what gets stored alongside each request-lifecycle event), persistence design (Task 2's layered validation/transaction work), and later reporting/traceability work — getting this wrong after other modules are built means retrofitting audit calls everywhere instead of designing them in from the start. | The confirmed set of fields required per audit entry (actor/user, action, timestamp, affected entity/request ID, before/after values where relevant) and how long audit records need to be retained. | Audit logging gets added inconsistently per-module late in development, producing exactly the kind of "unnecessary changes to unrelated areas" NFR-010 is meant to prevent, and potentially leaving some lifecycle actions unaudited in violation of NFR-009. | Open