## Sheet1
Risk Register
Risk Priority Matrix: |  |  |  |  | Probability
Low Priority <= 2 |  |  |  |  | Low | Medium | High
Medium Priority > 2 & <=5 |  |  |  | Low | Low | Low | Medium
High Priority >5 |  | Impact |  | Medium | Low | Medium | High
|  |  |  | High | Medium | High | High
Risk ID | Description | Cause | Probability | Impact | Priority | Mitigation | Contingency | Owner | Status
R-001 | Teammate unable to work, Max 3-person team constraint | Poor Health/Unfortunate Unforeseen Complications | Medium | High | High | Cross training so other teammates can pick up slack. | Unable to add team members to project. Remaining teammates will have to work under increased load to make up for lack of teammate until situation can be rectified. Otherwise, renegotiation with stakeholders about replacement team member under severe complications. | Project Team | Open
CON-003
R-002 | Unrealistic Scope, Scope Constraint and Time Constraint, if CON-001 is not adhered to. | Team may become too ambitious in defining the scope so as to create too much work resulting in the project not being able to be completed in the allocated time | Medium | High | High | Team must agree on scope that meets base stakeholder expectations and requirements. Such as a MVP (Minimal Viable Product) If this is noticed to be achievable during later stages improvement of scope to enhance product with nice to haves can be considered under strict change control processes. | If initial scope is found to be too much change control processes must be followed to reduce scope so that unnecessary items that are not needed for the success of the project can be eliminated. | Stakeholder and Scope Lead | Open
R-003 | FS-003 Built system may use technologies that are incompatible with external system making it unable to integrate | Lack of consideration of integration between systems when designing the system and choosing the technologies and architecture to be used. | Low | High | Medium | Team must take into consideration the integration into the full system and make the decisions regarding design based on constraints and requirements and ensure that technologies can work together. | Project system will have to be reworked so that it will be able to integrate however this will impact time constraint heavily as the project will fail to be completed in time resulting in failure. | Stakeholder and Scope Lead. | Open
Built system may use technologies that are incompatible with external system making it unable to integrate
R-004 | ASM-006 | Stakeholder unavailability | Medium | Medium | Medium | Make the interactions with stakeholders meaningful so that information gained is sufficient if it comes down to them being unavailable | Team may need to conduct its own research into the company with lack of stakeholders but may not be as effective as actual stakeholder engagement. | Project Team | Open
Suitable stakeholders may not be frequently available to clarify needs and review the team’s interpretation of the CivicConnect process.
R-005 | CON-006 | Lack of defined user roles and responsibilities. | Low | High | Medium | Proper stakeholder engagement to create well-defined user roles. | Research into similar platforms to identify roles and the responsibilities and access they have. | Requirements and Security Lead. | Open
ASM-004
Security may be impacted and requester may be able to complete tasks they should not and access information they should not.
R-006 | SC-002 | Categories are not well defined and derived from relevant stakeholders. | Low | Medium | Low | Sufficient engagement with stakeholders to derive relevant proper categories. | Research into the types of requests users usually make using old data from CivicConnect if stakeholders aren’t available. To derive proper categories. | Stakeholder and Scope Lead. | Open
ASM-002
FR-002
Service request categories may be insufficient or irrelevant resulting in could cause requests to be misclassified and make reports unreliable.
R-007 | SC-004 | Request statuses and lifecycle phases are ill-defined. | Low | Medium | Low | Significant engagement with stakeholders to derive well defined request statuses, lifecycle and workflow. | Research and observation of CivicConnect working environment to discover and understand workflows to create a meaningful system in the absence of stakeholder help and engagement. | Requirements Lead | Open
ASM-003
FR-003
Request statuses and request lifecycle phases are ill-defined resulting in system creation that may not meet needs or expected workflow.
R-008 | ASM-001 | Stakeholders might lack the resources to access platform and team did not cater to this. | Low | Low | Low | When designing and implementing choose relevant tech stacks and architecture so that the app is easily available to most requesters. Possible implementation of offline system in case of some requesters not having the basic resources needed which is unlikely. | Development making the system available offline which is unlikely. | Requirements Lead | Open
FS-001
Requester may not have access to a suitable device, supported browser and sufficiently reliable internet connection when using CivicConnect.
Please note this is deferred scope and not a priority.
R-009 | AI-assisted content may contain unverified or incorrect assumptions if not independently checked | Team member negligence is verifying ai generated work. | Low | Medium | Low | Governance through github makes it that work needs to have two reviewers who have to sign off on the merge so this can be detected and rejected by other teammates. | If teammate refuses to fix it other teammates will have to take over work and inform relevant stakeholders so that teammate can be dealt with. | Project Team. | Open
R-010 | Incorrect or prematurely enabled Supabase RLS rules could allow unauthorised access to CivicConnect data or block users who should have access. | The team has limited experience with Supabase RLS, while authentication, role mapping and live database integration are not complete yet. | Medium | High | High | Keep RLS disabled until authentication, role mapping and live database integration are ready. Define and test requester, staff and management policies before enabling it. | Disable or roll back faulty policies, restrict affected access, correct the rules and retest before enabling RLS again. | Project Team | Open
R-011 | Supabase may become unsuitable if CivicConnect later needs more complex backend processing. | The current stack assumes that the required backend features can be handled using Supabase, PostgreSQL functions and Edge Functions where needed. | Low | High | Medium | Review backend requirements as development continues and keep the technology decision and Node.js/Express alternative documented in ADR-001. | Reconsider the backend and introduce Node.js/Express if later requirements justify it. | Project Team | Open
R-012 | Dependency or version problems could cause development, build or testing failures. | React, Vite, Node.js, Vitest, the Supabase client and other project dependencies have compatibility requirements that must remain aligned. | Medium | Medium | Medium | Use compatible locked versions and GitHub Actions Client CI to run npm ci, tests, lint and build checks on changes before integration. | Update or roll back incompatible dependencies and rerun the required CI checks before integration. | Project Team | Open
R-013 | Incorrect deployment environment configuration could connect the frontend to the wrong Supabase project or prevent the application from connecting. | Environment-specific values may be configured incorrectly when Vercel/Supabase environments are introduced. | Medium | Medium | Medium | Keep environment values separate, document VITE_SUPABASE_URL and VITE_SUPABASE_ANON_KEY, and verify configuration during deployment testing. | Correct the affected environment configuration, redeploy, and repeat the deployment checks before promotion. | Project Team | Open
R-014 | A privileged Supabase secret/service key could be exposed in frontend code or committed to the repository. | A team member could incorrectly use a privileged key in browser code or source-controlled configuration. | Low | High | High | Never place privileged Supabase secrets in the React frontend or repository. Use only browser-safe configuration in the client and controlled server-side secret storage if later required. | Revoke/rotate the exposed credential immediately, remove it from active configuration, review repository history and verify access controls before continuing. | Project Team | Open
R-015 | Vercel or Supabase availability, service limits or pricing changes could affect CivicConnect. | The selected deployment direction depends on externally hosted services and current plan limits. | Medium | Medium | Medium | Review current provider limits and expected usage before production, and keep the documented hosting alternative available for reconsideration. | Reassess hosting/provider plans, reduce resource use where practical, or move to the documented alternative if the selected service becomes unsuitable. | Project Team | Open
R-016 | The application may build successfully but authentication, routing or access control could behave differently after deployment. | Local verification does not fully prove behaviour in the deployed environment, especially while Auth, live persistence and RLS are incomplete. | Medium | Medium | Medium | Test the deployed application, authentication, role access and important user flows before production promotion. | Block production promotion, correct the deployment/integration issue and rerun deployment-level verification. | Project Team | Open
R-017 | CI checks may fail or become unreliable as the project structure and dependencies change. | M2-12 introduces repeatable automated build/test/lint checks that depend on the current React/Vite project and dependency configuration. | Medium | Medium | Medium | Keep CI aligned with the implemented project, use locked dependencies, and review CI results before integration. | Fix the workflow or affected project configuration, rerun the checks, and do not treat a failing required check as successful evidence. | Project Team | Open
R-018 | Changes could be integrated without enough independent review or visible verification evidence. | The small team relies on branches, Pull Requests, reviewer approvals and visible CI results to control integration. | Medium | High | High | Use the agreed branch/PR workflow, require the planned independent reviews for substantive changes, and keep CI results visible to reviewers. | Stop or revert the integration, obtain the required review, correct the issue and rerun verification before re-integration. | Project Team | Open
R-019 | Initial CivicConnect functionality may not yet represent the final persistence, authentication and access-control behaviour. | M2-13 begins meaningful implementation, but some production-facing integration work remains incomplete at this stage. | Medium | High | High | Keep current limitations documented and progressively replace temporary/local behaviour with the approved Supabase persistence, authentication and role/RLS controls. | Do not promote incomplete functionality as production-ready; complete and verify the missing integration before production use. | Project Team | Open
R-020 | Technical documentation may become inconsistent with the application as implementation changes. | M2-13 requires README and technical documentation to remain aligned with the repository/application during active development. | Medium | Medium | Medium | Update technical documentation in the same development cycle as meaningful implementation changes and review it during Pull Requests. | Correct the affected documentation before milestone/release sign-off and link the corrected evidence to the relevant issue/PR. | Project Team | Open
R-021 | Notification delivery/read history is not retained — the system has no record of whether or when a requester actually saw an update | ADR-007: no dedicated Notification entity; relies on current status + history only | Low | Low | Low | Ensure the current-status view is always accurate and easy to find, so absence of a delivery log matters less in practice | If a dispute arises over "was I told," rely on request_status_history.changed_at as the closest available evidence, and reassess ADR-007 if this becomes a recurring problem | Persistence/Data lead | Open
R-022 | A breaking change to the REST API's request/response shape could silently break a client before a versioning scheme exists | ADR-008: no API versioning mechanism defined yet; single client assumed for now | Medium | Medium | Medium | Keep request/response shapes additive-only while only one client exists | Introduce explicit API versioning before a second independently-deployed client is added | Integration lead | Open
R-023 | A notification may never fire if the application process crashes after the status update commits but before the in-process event is raised | ADR-009: notification delivery is tied to the live application process and is not persisted or queued | Low | Medium | Low | Fire the event as close as possible to the transaction commit in the same logical operation, minimizing the failure window | If missed notifications become noticeable, reassess ADR-009 toward a durable/queued event mechanism rather than pure in-process | Integration lead | Open
R-024 | Migrating away from Supabase would require non-trivial schema/data migration effort, beyond the availability/backup concerns already tracked in R-011 | ADR-005: schema is defined against Supabase/PostgreSQL specifically; creates platform dependency | Low | Medium | Low | Prefer standard PostgreSQL features over Supabase-proprietary ones where practical, to keep a migration path open | If Supabase becomes unsuitable (cost, limits, deprecation), migrate to another managed PostgreSQL provider using the same relational schema | Persistence/Data lead | Open