## RTM
Source and Scope ID | Requirement ID | Requirement Summary | Type | Priority | Acceptance Criteria ID | ASR Link | Architecture | Persistence Impact | Design Decision | Technology Decision | Implementation evidence | Verification evidence | Status | ADR | M4 acceptance assessment | Outstanding evidence / final action | M1 acceptance criterion (verbatim)
ST-001 / SC-001, SC-003 | FR-001 | Submit Service Request | Functional | Must | AC-FR-001 | NFR-001 Performance; NFR-004 Data Integrity; NFR-005 Reliability | Modular Monolith (M2-03): Request Processing module → Data Persistence module | public.service_requests (requester_id, reference_number, title, description, category, status, timestamps); unique reference-number constraint. | DIP: Request Processing depends on an interface, not a concrete class (Design Problem 1) (persistence interface) | M2-10/M2-11: React + Vite frontend; Supabase backend/database services; Vercel deployment direction. | M4 final: RequestForm.jsx; requestService.js; Supabase request repository; service_requests; unique reference generated and displayed. | BB-02 (TestEvidenceCivicconnect(3), pp.4–6); E2E-01; request service/repository automated tests. | Implemented — evidenced | ADR-008, ADR-001 | Met - evidenced | Evidence linked to saved request and unique reference confirmation. | Given a requester has entered all required information, when the request is submitted successfully, then it is saved, and a unique reference number is displayed.
ST-001 / SC-002 | FR-002 | Categorise Service Request | Functional | Must | AC-FR-002 | NFR-004 Data Integrity | Modular Monolith (M2-03): Request Processing module (validation) → Data Persistence module | service_requests.category uses controlled public.request_category values. | DIP: Request Processing depends on an interface, not a concrete class (Design Problem 1) (persistence interface) | M2-10/M2-11: React + Vite frontend; Supabase backend/database services; Vercel deployment direction. | M4 final: Requester form controlled category selector; service_requests.category and request_category enum/constraints. | BB-02 (pp.4–5: required category and saved request); E2E-01. | Implemented — evidenced | ADR-001 | Met - evidenced | Category selection and persistence demonstrated in the existing request evidence. | Given the approved category list is available, when a requester creates a request, then one category can be selected and saved with the request.
ST-001 / SC-004 | FR-003 | View Request Status | Functional | Must | AC-FR-003 | NFR-001 Performance; NFR-002/003 Security | Modular Monolith (M2-03): Request Processing module → Data Persistence module | Select service_requests by requester_id | DIP: Request Processing depends on an interface, not a concrete class (Design Problem 1) (persistence interface) | M2-10/M2-11: React + Vite frontend; Supabase backend/database services; Vercel deployment direction. | M4 final: Requester request-details/status UI; request read service/repository; current service_requests.status. | BB-05 (pp.13–15: displayed status/history); E2E-01. | Implemented — evidenced | ADR-008, ADR-001 | Met - evidenced | Current status shown for a saved request. | Given a requester has submitted a request, when they open it, then its current approved status is displayed.
ST-001 / SC-005 | FR-004 | View Request History | Functional | Should | AC-FR-004 | NFR-009 Auditability; NFR-002/003 Security | Modular Monolith (M2-03): Request Processing module → Data Persistence module | Read service_requests by authenticated requester_id (previous requests); request_status_history supports per-request lifecycle detail. | DIP: Request Processing depends on an interface, not a concrete class (Design Problem 1) (persistence interface) | M2-10/M2-11: React + Vite frontend; Supabase backend/database services; Vercel deployment direction. | M4 final: Requester My Requests/history and request-details screens; queries filtered to authenticated requester. | E2E-01 (requester lifecycle); BB-02/03 navigation screenshots, pp.5–7. Confirm final history-list screenshot in evidence index. | Implemented — evidenced | ADR-005, ADR-008, ADR-001 | Met - evidenced | Requester history workflow previously exercised; add a labelled My Requests history screenshot if available. | Given a requester has previous requests, when they open their history, then those requests and their reference numbers are shown.
ST-001 / SC-006 | FR-005 | Receive Request Notifications | Functional | Should | AC-FR-005 | NFR-010 Maintainability | Modular Monolith (M2-03): Notifications module (triggered by Request Processing module) | public.notifications (recipient_user_id, service_request_id, event_type, read_at); public.notify_request_comment trigger plus existing observer functions. | Strategy: separate status-transition and notification behaviours (Design Problem 2); DIP: Notifications depends on an interface, not a concrete class (Design Problem 1) | M2-10/M2-11: React + Vite frontend; Supabase backend/database services; Vercel deployment direction. | M4 final: NotificationBell.jsx and notification read/mark-as-read operations; notifications table; status/comment notification observers and triggers. | BB-04 (pp.8–11; requester 'New Comment' notification); E2E-01; notification observer unit tests (2). Status-specific notification matrix not fully attached. | Implemented — final AC evidence to link | ADR-007, ADR-009, ADR-001 | Met - team recorded; evidence check pending | Link acceptance evidence for each approved status-triggered notification; comment event is evidenced. | Given a tracked request changes to an approved notification-triggering state, when the update is saved, then the relevant user can see an in-app notification.
ST-002 / SC-007 | FR-006 | View Assigned Requests | Functional | Must | AC-FR-006 | NFR-002/003 Security (RBAC boundary); NFR-001 Performance | Modular Monolith (M2-03): Request Processing module → Data Persistence module | Select service_requests by assigned_staff_id | DIP: Request Processing depends on an interface, not a concrete class (Design Problem 1) (persistence interface) | M2-10/M2-11: React + Vite frontend; Supabase backend/database services; Vercel deployment direction. | M4 final: Staff Dashboard, assigned-request services/repositories, assignment-filtered list; authenticated staff-role permissions. | E2E-01; BB-04 (p.11 staff dashboard); SEC-01–SEC-08 server-side role/ownership tests. | Implemented — evidenced | ADR-008, ADR-001 | Met - evidenced | Staff assignment visibility and authorised processing demonstrated. | Given an authorised staff member signs in, when they open their work list, then only requests available to their role or assignment are shown.
ST-002 / SC-008 | FR-007 | Search, Filter and Sort Requests | Functional | Should | AC-FR-007 | NFR-001 Performance; NFR-011 Scalability | Modular Monolith (M2-03): Request Processing module → Data Persistence module | Indexed public.service_requests queries; management requests_for_assignment(...) RPC with filters/pagination. | DIP: Request Processing depends on an interface, not a concrete class (Design Problem 1) (persistence interface) | M2-10/M2-11: React + Vite frontend; Supabase backend/database services; Vercel deployment direction. | M4 final: Staff request-list query and filtering controls; requests_for_assignment(...) exposes category/priority/staff/assignment filters for management. | Implemented per team final scope register; specific screenshot/test showing staff search, filter AND sort not included in uploaded test evidence. | Implemented — final AC evidence to link | ADR-008, ADR-001 | Met - team recorded; evidence check pending | Attach one final staff-side demonstration of search, filter and sort. Management filters alone do not prove staff sort. | Given requests exist, when authorised staff apply a search term, filter or sort order, then the displayed results match the chosen condition.
ST-002 / SC-009 | FR-008 | View Detailed Request Information | Functional | Must | AC-FR-008 | NFR-002/003 Security; NFR-001 Performance | Modular Monolith (M2-03): Request Processing module → Data Persistence module | Read service_requests, comments, request_status_history and request_assignments with role-based restrictions. | DIP: Request Processing depends on an interface, not a concrete class (Design Problem 1) (persistence interface) | M2-10/M2-11: React + Vite frontend; Supabase backend/database services; Vercel deployment direction. | M4 final: Role-protected requester/staff request-details pages; reads service_requests and related comments, status and assignment histories. | BB-03 (pp.6–7 unauthorised requester rejected); BB-05 (pp.13–16 details/history); E2E-01. | Implemented — evidenced | ADR-008, ADR-001 | Met - evidenced | Details display and access boundary demonstrated. | Given authorised staff select a request, when its details are opened, then all information recorded for that request is displayed.
ST-002 / SC-010 | FR-009 | Assign Responsibility | Functional | Must | AC-FR-009 | NFR-002/003 Security; NFR-009 Auditability | Modular Monolith (M2-03): Request Processing module → Data Persistence module | RPC updates service_requests.assigned_staff_id and maintains request_assignments (assigned_by, assigned_at, unassigned_at, reason). | DIP: Request Processing depends on an interface, not a concrete class (Design Problem 1) (persistence interface) | M2-10/M2-11: React + Vite frontend; Supabase backend/database services; Vercel deployment direction. | M4 final: Management assignment UI and restricted public.assign_request()/unassign_request() RPCs; active assignment and assignment history. | E2E-01; BB-05 (p.16 assignment history); SEC-01–SEC-08 (authenticated RPC and DB checks). | Implemented — evidenced | ADR-008, ADR-001 | Met - evidenced | Assignment, ownership restrictions and history supported by server-side evidence. | Given an unassigned or reassignable request exists, when an authorised user selects eligible personnel and confirms, then the responsible person is recorded.
ST-002 / SC-011, SC-016 | FR-010 | Update Request Status | Functional | Must | AC-FR-010 | NFR-004 Data Integrity; NFR-005 Reliability; NFR-009 Auditability; NFR-010 Maintainability | Modular Monolith (M2-03): Request Processing module (status workflow) → Notifications module + Data Persistence module | RPC updates service_requests.status and writes request_status_history with actor, old/new state, timestamp and note. | Strategy: separate status-transition and notification behaviours (Design Problem 2); DIP: Request Processing depends on an interface, not a concrete class (Design Problem 1) (persistence, notification interfaces) | M2-10/M2-11: React + Vite frontend; Supabase backend/database services; Vercel deployment direction. | M4 final: Staff/manager request status interface; restricted change_request_status() RPC with approved transitions. | BB-05 (pp.13–16 accepted→in progress→resolved and history); SEC-01–SEC-08 authenticated status/role checks. | Implemented — evidenced | ADR-005, ADR-008, ADR-009, ADR-001 | Met - evidenced | Approved workflow steps and history evidenced in tested paths. | Given a request is in a valid current state, when authorised staff select an allowed next status, then the new status and update time are recorded.
ST-002, ST-003 / SC-012, SC-016 | FR-011 | Record Actions and Comments | Functional | Must | AC-FR-011 | NFR-009 Auditability; NFR-002/003 Security | Modular Monolith (M2-03): Request Processing module → Data Persistence module | comments(service_request_id, author_user_id, comment_text, is_internal, date_created) + secured read policies. | DIP: Request Processing depends on an interface, not a concrete class (Design Problem 1) (persistence interface) | M2-10/M2-11: React + Vite frontend; Supabase backend/database services; Vercel deployment direction. | M4 final: Staff public comments and internal notes; requester replies; author_user_id and is_internal handling; timeline. | BB-04 (pp.8–10; public/internal notes, requester reply, dates); E2E-01. | Implemented — evidenced | ADR-008, ADR-001 | Met - evidenced | Staff notes, requester reply and displayed timestamps evidenced. | Given authorised staff are viewing a request, when they save a comment, action or progress note, then it appears in the request history with the responsible user and time.
ST-002 / SC-013, SC-016 | FR-012 | Resolve and Close Requests | Functional | Must | AC-FR-012 | NFR-004 Data Integrity; NFR-005 Reliability; NFR-009 Auditability | Modular Monolith (M2-03): Request Processing module (status workflow) → Notifications module + Data Persistence module | service_requests.status/resolved_at/closed_at/resolution_summary and request_status_history. | Strategy: separate status-transition and notification behaviours (Design Problem 2); DIP: Request Processing depends on an interface, not a concrete class (Design Problem 1) (persistence, notification interfaces) | M2-10/M2-11: React + Vite frontend; Supabase backend/database services; Vercel deployment direction. | M4 final: Controlled change_request_status() workflow; Resolved/Closed enum states and resolution/closure fields. | BB-05 (pp.13–16 shows Resolved and history); E2E-01. Distinct Closed completion screenshot/test is not in supplied evidence. | Implemented — final AC evidence to link | ADR-005, ADR-008, ADR-009, ADR-001 | Met - team recorded; evidence check pending | Attach a completed Closed transition and completion-information record to support the full 'resolve and close' criterion. | Given the approved completion conditions are met, when authorised staff resolve or close the request, then its final state and completion information are recorded.
ST-003 / SC-014, SC-015 | FR-013 | View Service Activity Dashboard | Functional | Could | AC-FR-013 | NFR-001 Performance; NFR-011 Scalability | Modular Monolith (M2-03): Request Processing module (reporting queries) → Data Persistence module | manager_summary() aggregates public.service_requests and staff_current for operational counts. | DIP: Request Processing depends on an interface, not a concrete class (Design Problem 1) (persistence interface) | M2-10/M2-11: React + Vite frontend; Supabase backend/database services; Vercel deployment direction. | M4 final: Management Dashboard, manager_summary() aggregation and manager workflow UI. | Functional dashboard previously demonstrated/reported; no current labelled AC-FR-013 dashboard screenshot in TestEvidenceCivicconnect(3). | Implemented — final AC evidence to link | ADR-001 | Met - team recorded; evidence check pending | Attach management dashboard screenshot with activity counts reconciled against current stored data. | Given service-request data exists, when a management user opens the dashboard, then the agreed activity measures are displayed using current stored data.
ST-003 / SC-014 | FR-014 | Monitor Open and Overdue Requests | Functional | Must | AC-FR-014 | NFR-001 Performance; NFR-011 Scalability | Modular Monolith (M2-03): Request Processing module (reporting queries) → Data Persistence module | Service request status/due_at aggregates; team_overview() and requests_for_assignment() filter active/overdue/assigned requests. | DIP: Request Processing depends on an interface, not a concrete class (Design Problem 1) (persistence interface) | M2-10/M2-11: React + Vite frontend; Supabase backend/database services; Vercel deployment direction. | M4 final: Manager dashboard and Team Overview; manager_summary(), team_overview(), requests_for_assignment() RPCs. | Management workflow implemented/reported; no complete open/overdue/resolved/closed comparison screenshot attached. | Implemented — final AC evidence to link | ADR-001 | Met - team recorded; evidence check pending | Attach monitoring evidence covering all four classes: open, overdue, resolved and closed. | Given requests have different statuses and due conditions, when a management user selects a monitoring view, then open, overdue, resolved and closed requests can be identified.
ST-003, ST-004 / SC-015 | FR-015 | Generate Reporting and Analysis Information | Functional | Must | AC-FR-015 | NFR-001 Performance; NFR-011 Scalability | Modular Monolith (M2-03): Request Processing module (reporting queries) → Data Persistence module | management_report() aggregates request data with category/date filters; SQL in 20261016090506_management_reports.sql. | DIP: Request Processing depends on an interface, not a concrete class (Design Problem 1) (persistence interface) | M2-10/M2-11: React + Vite frontend; Supabase backend/database services; Vercel deployment direction. | M4 final: Management reports page; management_report(start_date,end_date,category) RPC and management_reports migration. | Management reporting implemented/reported; no final report output proving category, status, resolution rate and workload dimensions in uploaded test evidence. | Implemented — final AC evidence to link | ADR-001 | Met - team recorded; evidence check pending | Attach final report screenshot/output with selected filters, resolution rate and workload measures. | Given service-request data exists, when a management user requests a report, then statistics are calculated using the selected category, status, resolution-rate or workload information.
M1 quality / performance | NFR-001 | Performance | Non-functional | Not assigned in M1 | AC-NFR-001 | FR-001, FR-003, FR-006–008, FR-013–015 | Cross-cutting: core request submission, read and management workflow; performance under load. | Indexes and query performance over service_requests, assignment/history records. | M1 quality/constraint baseline; final acceptance and residual risk kept separate from functional delivery. | React + Vite and Supabase/PostgreSQL; deployed managed hosting. | Existing functional execution verifies correctness, not 95th-percentile latency. | AC-NFR-001 requires >=95% of selected actions <=3 s under agreed expected load; no recorded performance sample. | Not yet verified | Review existing ADRs — do not invent IDs | Not verified | Agree load profile and capture timed results with sample size and percentile. | A performance test under the agreed expected load shows that at least 95% of the selected main actions complete within three seconds.
ST-004, ST-005 / SC-017 | NFR-002 | Security and access control | Non-functional | Not assigned in M1 | AC-NFR-002 | FR-003, FR-006, FR-008–011; SC-017 | Cross-cutting: AuthProvider/ProtectedRoute, Supabase RLS and restricted RPC/Edge Function. | RLS policies, grants and SECURITY DEFINER functions restrict request and staff access. | M1 quality/constraint baseline; final acceptance and residual risk kept separate from functional delivery. | Supabase Auth, PostgreSQL RLS/RPC and Edge Functions. | Backend permission hardening; staff onboarding admin check; request ownership checks. | BB-03; SEC-01–SEC-08 authenticated RPC cases; SEC-09 403; E2E-02A–C. | Verified — tested scope | Review existing ADRs — do not invent IDs | Verified - tested scope | Attach SEC-09 to controlled evidence; full fresh-database RLS/grant parity remains OPS-01. | Role-based access tests confirm that every tested role can access its permitted functions and cannot access restricted functions or information.
ST-004, ST-005 / SC-017 | NFR-003 | Privacy | Non-functional | Not assigned in M1 | AC-NFR-003 | FR-003, FR-006, FR-008, FR-011 | Cross-cutting: requester/staff data access and internal note separation. | Private request/notes through requester-scoped queries and RLS; staff-only comments. | M1 quality/constraint baseline; final acceptance and residual risk kept separate from functional delivery. | Supabase Auth/RLS; privacy-conscious data capture. | Public/internal note model, requester record filtering and author handling. | BB-03 requester denied another request; BB-04 internal note not displayed to requester; full field minimisation review absent. | Partially verified | Review existing ADRs — do not invent IDs | Partially verified | Review fields/forms against approved personal-data minimisation and record permission matrix. | A review of forms, permissions and stored fields confirms that only approved information is collected and unauthorised roles cannot view protected information.
M1 quality / SC-011, SC-016 | NFR-004 | Data integrity | Non-functional | Not assigned in M1 | AC-NFR-004 | FR-001, FR-002, FR-010, FR-012 | Validation layer plus database constraints and server-side status workflow. | Required DB fields; enum/check/foreign keys; restricted status transitions and history. | M1 quality/constraint baseline; final acceptance and residual risk kept separate from functional delivery. | PostgreSQL integrity constraints; authorised change_request_status RPC. | Reference uniqueness, mandatory fields and state transition controls built. | BB-01/BB-02 form validations; BB-05 state changes; SEC-01–SEC-08 negative permissions; DB length boundary not fully checked. | Partially verified | Review existing ADRs — do not invent IDs | Partially verified | Confirm direct-DB rejection of incomplete records and invalid transitions; TD-06 tracks remaining DB input limits. | Validation tests reject incomplete required records and status changes that are not allowed by the approved workflow.
ST-001 / SC-001, SC-005 | NFR-005 | Reliability and recovery | Non-functional | Not assigned in M1 | AC-NFR-005 | FR-001, FR-010, FR-012 | Frontend error feedback, durable Supabase persistence and retry/recovery behaviour. | Durable service_requests persistence; nonduplicating submission/retry behaviour not fully evidenced. | M1 quality/constraint baseline; final acceptance and residual risk kept separate from functional delivery. | Supabase PostgreSQL; React service/repository error handling. | Existing request persistence/reopen and staff invitation recovery (separate workflow). | BB-02 saved request and E2E-01 reopen supported; no simulated recoverable failure with duplicate check documented. | Partially verified | Review existing ADRs — do not invent IDs | Partially verified | Record refresh persistence and one simulated recoverable request-submission failure with duplicate verification. | A successfully saved request remains available after refresh and a simulated recoverable failure gives the user a clear message without creating an unintended duplicate.
ST-001 / SC-001, SC-004 | NFR-006 | Usability | Non-functional | Not assigned in M1 | AC-NFR-006 | FR-001, FR-003, FR-004 | Requester submission and tracking pages, form hints and feedback. | No special persistence; usability evidence concerns observation of first-time use. | M1 quality/constraint baseline; final acceptance and residual risk kept separate from functional delivery. | React/Vite UI. | Clear labels, field validation, confirmation feedback implemented. | BB-01/BB-02 screenshots show form feedback, but no representative first-time-user walkthrough record. | Not yet verified | Review existing ADRs — do not invent IDs | Not verified | Obtain representative first-time user task observation, issues and resolution/acceptance. | Representative first-time users can complete the agreed submission and tracking walkthrough, and any blocking usability problems are recorded and corrected or accepted.
ST-001 / SC-001, SC-004 | NFR-007 | Accessibility | Non-functional | Not assigned in M1 | AC-NFR-007 | FR-001, FR-003, FR-004 | Keyboard support, labelled inputs and contrast in core requester workflows. | No special DB component. | M1 quality/constraint baseline; final acceptance and residual risk kept separate from functional delivery. | Frontend accessibility/HTML/CSS checks. | Accessible-input intentions in UI; no structured audit supplied. | No recorded keyboard-only and contrast assessment. | Not yet verified | Review existing ADRs — do not invent IDs | Not verified | Record keyboard navigation, accessible labels and colour-contrast check for selected core screens. | The agreed core screens can be operated by keyboard, controls have understandable labels and the selected contrast check passes.
ST-001 / SC-001, SC-004 | NFR-008 | Compatibility | Non-functional | Not assigned in M1 | AC-NFR-008 | FR-001, FR-003, FR-004 | Core screens on selected desktop/mobile browsers and device sizes. | No special DB component. | M1 quality/constraint baseline; final acceptance and residual risk kept separate from functional delivery. | React/Vite frontend and hosting/browser support. | Responsive UI screens supplied, but no approved browser/device list verification. | Existing mobile-layout screenshots do not demonstrate all agreed browsers. | Not yet verified | Review existing ADRs — do not invent IDs | Not verified | Approve target browser/device list and record pass/fail for each core workflow. | The agreed core workflows pass on every browser and screen size listed in the approved compatibility list.
ST-002, ST-003 / SC-016 | NFR-009 | Auditability | Non-functional | Not assigned in M1 | AC-NFR-009 | FR-004, FR-009–012; SC-016 | Request-status and assignment histories, comment authorship and timestamps. | request_status_history, request_assignments, comments, audit_log. | M1 quality/constraint baseline; final acceptance and residual risk kept separate from functional delivery. | Supabase/PostgreSQL triggers, audit tables and restricted RPCs. | Status/assignment append-only history; actor/time metadata. | BB-04 time-stamped comments; BB-05 pp.14–16 status/assignment history; E2E-01. | Verified — tested scope | Review existing ADRs — do not invent IDs | Verified - tested scope | Confirm any remaining approval-defined lifecycle actions are covered by audit evidence. | Tests confirm that each approved lifecycle action records the action, date and responsible user where applicable.
M1 quality / team constraints | NFR-010 | Maintainability | Non-functional | Not assigned in M1 | AC-NFR-010 | FR-005, FR-010, FR-012 | Modular client services, repository boundaries and documented migrations. | Schema migrations and audited SQL/RPC boundaries; migration parity open. | M1 quality/constraint baseline; final acceptance and residual risk kept separate from functional delivery. | React/Vite modules, GitHub PRs, ESLint/Vitest. | Modular folders/services; documented ADRs; multiple unit suites. | Local ESLint PASS, Vitest 80 PASS / 3 skipped, Vite build PASS; formal team standards/document review not linked. | Partially verified | Review existing ADRs — do not invent IDs | Partially verified | Link exact-commit CI and team code/docs review; preserve migration reproducibility finding TD-02. | The project structure and developer documentation are reviewed against the team standards, and automated checks pass for the changed area.
ST-004 / capacity constraint | NFR-011 | Scalability and capacity | Non-functional | Not assigned in M1 | AC-NFR-011 | FR-007, FR-013–015 | Service request queries/indexes and managed database/hosting limits. | Database indexes assist lookup, but cannot establish capacity at expected volume. | M1 quality/constraint baseline; final acceptance and residual risk kept separate from functional delivery. | Supabase managed PostgreSQL/Vercel deployment. | Existing indexes and paginated query patterns. | No agreed-volume capacity/load test supplied. | Not yet verified | Review existing ADRs — do not invent IDs | Not verified | Agree volume/throughput assumptions and perform justified test without loss of core functionality. | A capacity test using the agreed volume estimates completes without loss of core functionality or failure of the request process.
ST-004 / CON-004 | NFR-012 | Cost | Non-functional | Not assigned in M1 | AC-NFR-012 (missing in PED) | CON-004; platform deployment | Architecture hosting selection and deployment-operations planning. | Database usage/storage, authentication email and operational limits affect cost. | M1 quality/constraint baseline; final acceptance and residual risk kept separate from functional delivery. | Low-cost/managed React/Vercel/Supabase setup. | Free/low-cost baseline described in PED; actual budget/tier comparison not supplied. | PED NFR-012 defines cost, but no AC-NFR-012 appears in uploaded Section A criteria list. | Criterion missing / not verified | Review existing ADRs — do not invent IDs | Criterion missing / not verified | Agree missing AC-NFR-012 and verify hosting tiers, limits and project budget; do not invent approved criterion. | NOT DEFINED IN UPLOADED PED v4 — AC-NFR-012 absent from the Section A acceptance-criteria list. Team must agree wording and trace evidence.

## M4 Summary
CIVICCONNECT ¦ FINAL M4 REQUIREMENTS TRACEABILITY
Updated original M2 RTM — final implementation recorded separately from acceptance evidence and production readiness
FINAL RELEASE AND EVIDENCE GATES
Gate | Condition | Current status | Release follow-up
G-01 | Staff invitation + recovery | PASS — E2E-02A/B/C + SEC-09 | Archive post-fix screenshots with controlled test record.
G-02 | Management RPC authorisation | PASS — SEC-01–08 | Security regression evidence exists; ensure final commit matches tested DB.
G-03 | Fresh database migrations / RLS parity | OPEN (TD-02) | Validate complete schema/privileges and legacy migration ordering on disposable instance.
G-04 | Exact-release CI + 3 integration tests | OPEN (TD-04) | 80 local unit tests passed, 3 environment tests skipped; link actual GitHub Actions run.
G-05 | Small performance/security/operations evidence | OPEN | AC-NFR-001 capacity timing, dependency/secret check and backup/recovery.
PROPOSED M4 DECISION: Conditional Go for controlled academic demonstration; no public production Go until outstanding deployment/operational gates are verified.

## Scope Coverage
M1 IN-SCOPE CAPABILITY → FINAL REQUIREMENT/EVIDENCE TRACE
Every original SC-001–SC-017 remains visible. 'Review' indicates an evidence/acceptance gap, not a proven implementation failure.
M1 scope ID | Scope commitment | FR / NFR trace | Team-recorded delivery | Evidence trace | Final acceptance position | Remaining action
SC-001 | Submit new service request | FR-001 | Implemented | BB-02; E2E-01 | Evidenced | —
SC-002 | Select controlled request category | FR-002 | Implemented | BB-02; E2E-01 | Evidenced | —
SC-003 | Show confirmation and unique reference | FR-001 | Implemented | BB-03 p.6; E2E-01 | Evidenced | —
SC-004 | View current request status | FR-003 | Implemented | BB-05; E2E-01 | Evidenced | —
SC-005 | View previous requests | FR-004 | Implemented | E2E-01; My Requests UI | Evidenced (add image link) | Label a requester history-list screenshot in controlled evidence.
SC-006 | Meaningful requester feedback | FR-005 | Implemented | BB-04 comment notification; notification triggers | Review complete AC | Show all approved status-triggered notification cases.
SC-007 | Staff see relevant requests | FR-006 | Implemented | E2E-01; BB-04 p.11; SEC | Evidenced | —
SC-008 | Staff search, filter, sort | FR-007 | Implemented | Team scope calculator; filters implemented | Review complete AC | Attach staff search, filter and sort screenshot/demo.
SC-009 | Staff view request details | FR-008 | Implemented | BB-03; BB-05; E2E-01 | Evidenced | —
SC-010 | Assign or accept responsibility | FR-009 | Implemented | BB-05 p.16; E2E-01; SEC-01–08 | Evidenced | —
SC-011 | Controlled status transition | FR-010 | Implemented | BB-05; SEC regression | Evidenced | —
SC-012 | Record actions/comments/resolution info | FR-011, FR-012 | Implemented | BB-04; BB-05 | Review close evidence | Add Closed completion info to existing Resolved evidence.
SC-013 | Resolve/close requests | FR-012 | Implemented | BB-05 Resolved path | Review complete AC | Confirm Closed action and persisted completion info.
SC-014 | Monitor activity/open/overdue/resolved/closed | FR-013, FR-014 | Implemented | Manager Dashboard, manager_summary | Review complete AC | Attach management dashboard and four-state monitoring evidence.
SC-015 | Management statistics by category/status | FR-013, FR-015 | Implemented | management_report(); report page | Review complete AC | Attach report output for resolution rate/workload and selected filters.
SC-016 | Lifecycle action/status audit trail | FR-010, FR-011, FR-012; NFR-009 | Implemented | BB-04/BB-05; E2E-01 | Evidenced (tested paths) | Final coverage of all approved actions remains a review point.
SC-017 | Role-based access to functions/data | NFR-002; FR-006, FR-008, FR-009, FR-010 | Implemented | BB-03; SEC-01–09; E2E-02 | Verified tested scope | Database RLS/migration parity remains OPS-01.
EXCLUSIONS — NOT FAILED SCOPE (PED Section A)
FS-001–FS-007 | M1 explicitly deferred future scope | Outside committed original release | Still deferred | PED Section A future-scope baseline | Excluded from completion denominator | FS-002 is NOT implemented by email account registration.
OS-001–OS-005 | Original system-boundary exclusions | Outside committed original release | Out of scope | PED Section A system boundary | Excluded from completion denominator | Not failures of implementation.

## Evidence Index
M4 CONTROLLED EVIDENCE INDEX ¦ Do not claim evidence not attached
Pointers to supplied artefacts and confirmed test outcomes; add GitHub artifact links and missing screenshots before submission.
Evidence ID | Category | Recorded outcome | Controlled source / location | What it demonstrates | RTM coverage | Qualification / action
BB-01 | Manual black-box | PASS | TestEvidenceCivicconnect(3).docx pp.1–3 | Registration invalid email/password; successful confirmation | FR-001 contextual; NFR-004, NFR-006 | Evidence provided; this is frontend validation, not DB boundary proof.
BB-02 | Manual black-box | PASS | TestEvidenceCivicconnect(3).docx pp.4–5 | Required request fields; valid title and saved request | FR-001, FR-002, NFR-004 | Title-length acceptance does not establish DB max-length constraint.
BB-03 | Manual black-box | PASS | TestEvidenceCivicconnect(3).docx pp.6–7 | Confirmation/reference and requester cross-account restriction | FR-001, FR-008, NFR-002/003 | Request-level denial demonstrated; does not prove all RLS policies.
BB-04 | Manual black-box | PASS | TestEvidenceCivicconnect(3).docx pp.8–11 | Public/internal notes, requester reply, comment notification | FR-005, FR-011, NFR-003, NFR-009 | Comment notification evidenced; full status-event matrix remains unlinked.
BB-05 | Manual black-box | PASS | TestEvidenceCivicconnect(3).docx pp.12–16 | Accepted→In Progress→Resolved and ordered histories | FR-010, FR-012, NFR-004/009 | Closed final-state evidence not clearly provided.
E2E-01 | End-to-end | PASS | PED v4 Section C.4; verified project workflow | Requester→manager→staff request lifecycle, comments, notifications, assignment/history | FR-001–004, FR-006, FR-009–012 | Link final-version execution screenshot/demo and commit.
E2E-02A | Staff onboarding | PASS (user-confirmed) | Recent Add Staff success screenshot + manual outcome in chat | Brand-new staff account invitation, password and staff login | NFR-002; admin onboarding additional scope | Post-fix first-login screenshot not yet inserted in TestEvidenceCivicconnect(3).
E2E-02B | Staff recovery | PASS (user-confirmed) | Recent manual recovery email/password/login outcome in chat | Administrator recovery email, password setup, Staff Dashboard | NFR-002; TD-09 | Archive post-fix recovery sequence to controlled evidence.
E2E-02C | Dual-role account | PASS (user-confirmed) | Manual existing requester→staff testing in chat | One Auth identity with requester + staff profiles; staff routing | NFR-002; TD-08 | Add dual-role dashboard/permissions screenshots if required.
SEC-01–08 | Authenticated RPC security | PASS | TestEvidenceCivicconnect(3).docx pp.22–23 + verified SQL state in chat | Assignment/status positive & negative tests (manager/staff/admin) | FR-006, FR-009/010; NFR-002/004/009 | Associate tested environment and function versions with release commit.
SEC-09 | Edge Function security | PASS — HTTP 403 | Browser Console screenshot supplied in chat (not yet appended to evidence doc) | Non-admin staff denied resend_setup | NFR-002; TD-09 | Archive screenshot into controlled test evidence.
UT / Vitest | Local automated | PASS: 80 tests | PowerShell npm run test output in chat | 10 test files passed; 3 environment-dependent tests skipped | NFR-010 and relevant FR services | Capture local log/CI artifact for exact RC commit.
INT-04 | Real DB integration | REPORTED PASS: 3/3 | Teammate confirmation referred to in PED C.4 | Real-Supabase repository integration test execution | NFR-002/004/005 | Teammate screenshot and test-environment metadata still need linked.
Build / lint | Local automated | PASS with warning | PowerShell npm run lint and npm run build output in chat | ESLint clean; Vite bundle-size warning >500 kB | NFR-010 | Attach CI job for final commit; bundle-size work is low-priority debt.
OPS-01 | Clean migration and RLS parity | OPEN | PED C.6 / TD-02; prepared SQL migration files | Deployment and authorisation parity on fresh Supabase | NFR-002/005/010; release condition | Not proven; clean disposable deployment and configuration review required.
Perf/capacity | Non-functional check | NOT VERIFIED | No measured performance/capacity test in supplied evidence | p95 <=3 s expected-load target and approved capacity volume | NFR-001, NFR-011 | Run justified performance/capacity tests or formally record unverified acceptance.
M4 scope workbook | Team scope assessment | 15/15 FR recorded Met | CivicConnect Simplified Scope Calculation.xlsx | Team functional acceptance self-assessment | FR-001–015, SC-001–017 | Recorded statuses need stronger links for 6 FR criteria; not an independent test result.